## Skybot ver.1
Process | Test case | Step | Description | Status | Expected Result | Actual Result | Comment
Вступна частина (Introduction)
Our team conducts detailed testing of the functionality of the B2C portal stated in the requirements for a company engaged in the sale and service of electric transport (scooters) under the brand name Skybot in order to achieve the set business goals. "Skybot Electric Scooters" store located in Springfield, US. So portal is oriented for North America market. |  | test the requirements and ideas of the customer for the possibility of implementation | Analyze/evaluate incoming technical requirements | A detailed analysis of the requirements was created, discussed with the team, supplemented.
|  | Check and analyze the mockups of the portal | analyze the mockups for their relevance to the portal's theme | Created a mockup analysis, agreed |  |  | Link to mockups analysis: https://prometheus-qa.atlassian.net/browse/SBWP-10?focusedCommentId=10099
|  | Create checklists to test functionality | Creation of checklists for checking the functionality of (each individual) detailed requirement for the development of the portal of the online store of individual electric transport. | Created, discussed with the team, supplemented, finalized |  |  | Link to checklist: https://prometheus-qa.atlassian.net/browse/SBWP-10?focusedCommentId=10098
|  | Agree and receive standardized requirements from the customer (SRS-Software Requirements Specifications) |  | Agreed, received |  |  | Link to SRS: https://prometheus-qa.atlassian.net/browse/SBWP-10?focusedCommentId=10100
Вхідні критерії (Entry Criteria)
Conditions with which we can start testing:
Agreed requirements |  |  | Link to SRS: https://prometheus-qa.atlassian.net/browse/SBWP-10?focusedCommentId=10100 | Agreed, received
Checklist |  |  | Link to checklist: https://prometheus-qa.atlassian.net/browse/SBWP-10?focusedCommentId=10098 | Agreed, received
QA team |  |  | 40 QA specialists | Ready
Тest environment and tools |  |  | Will use simulators | Ready
Tests to be performed
Functional Testing
User Interface (UI) Testing
Compatibility Testing
Performance Testing
Security Testing
Payment Gateway Testing
Localization Testing
Usability Testing
Regression Testing Smoke testing
User Acceptance Testing (UAT)
Features not to be tested
Portal uptime
SQL backup frequency
(Test Deliverables) |  |  | Check-lists
Test cases
Bug reports
Fixes
Environments tests | Windows 10\11 test
Ubuntu 20+ test
MacOS Monterey test
Google Chrome
Microsoft Edge
Mozilla Firefox
Safari (нативно)
Android (9-14 versions)
IOS (14-17 versions)
Віртуальні сервери
| Feature KVM 1 |  | Processor - 2 vCPU Cores RAM - 8 GB RAM Disk Space - 100 GB NVMe Disk space Bandwidth - 2 TB Bandwidth Snapshot per week - 1 Snapshot Backup - Weekly Backups IP Address - Dedicated IP Address Management access - Full Root Access Support Assistant - AI Assistant
| Feature KVM 4 |  | Processor - 4 vCPU Cores RAM - 16 GB RAM Disk Space - 200 GB NVMe Disk space Bandwidth - 4 TB Bandwidth Snapshot per week - 1 Snapshot Backup -Weekly Backups IP Address - Dedicated IP Address Management access - Full Root Access Support Assistant - AI Assistant
Exit Criteria
Created and tested test cases
Maximum coverage of requirements were achieved
Regrettion test completed
Smoke tests completed
Bugs with high severity and priority were fixed
No critical bugs detected
User acceptance test done
Written bugreports
Risks and Contingencies
Resources issues |  | Risk: There is a small possibility that the qualifications and experience of the team will not be enough to conduct all the planned tests on time.
Contingency: All team members must constantly improve their qualifications, be present at all weekly sprints with a mentor, and in case of misunderstandings or unclear tasks, immediately contact more experienced colleagues.
Technical risks |  | Risk: There is a high risk of constant blackouts, interruptions with access to the Internet due to possible missile attacks by Russian terrorists
Contingency: Provide the team with alternative power sources (generators, power banks, battery stations...) and provide a high-speed Internet connection using GPON technology (optical fiber) or satellite Internet.
Communication and Feedback Channels: |  | Risk: change of requirements by the customer, when all tests have already been completed, but the project has not yet been declared for release
Contingency: Constantly maintain contact, communication with the customer and provide up-to-date information on the status and progress of testing.